## Timeline_milestones_quarters
Timeline - Biosphere Development, within 'Water Works' project, funded by People's Postcode Lottery's Dream Fund (Lead partner: Wildlife Trust BCN). Last updated: Cambridgeshire ACRE (MN), 2020.03.27 DRAFT
JULY 2018 - BIOSPHERE FEASIBILTY STUDY: Key work steams identified |  | Biosphere delivery within the Water Works project - Timeline, quarter by quarter - with key milestones
Work Category | Actions | Q1 (Apr-Jun 19) | Q2 (Jul-Sep 19) | Q3 (Oct-Dec 19) | Q4 (Jan-Mar 20) | Q1 (Apr-Jun 20) | Q2 (Jul-Sep 20) | Q3 (Oct-Dec 20) | Q4 (Jan-Mar 21) | ORIGINAL BUDGET HEADINGS(as listed by Cambs ACRE in stage 2 budget for Dream Fund)
1. Governance - Partnership development | Further develop current partnership membership & keep momentum |  |  | Number of new partners, representing new or under-represented stakeholder groups attracted to Steering Group |  |  |  | Full range of stakeholder groups represented on the Fens Biosphere Steering Group
| Ensure ongoing partnership input towards designation |  |  | Stakeholder engagement event/workshops held 18 Dec 2019 |  | Start of wider events & engagement programme, showcasing draft action plan for Fens Biosphere |  | Key stakeholder event planned on 11 Nov |  | Launch event [Note: due to slow traction with LPAs this has not been done]
2. Governance - Governance model development | Devise suitable governance structure & organisational arrangements, including partnership agreement |  |  | Terms of Reference for Fens Biosphere Steering Group adopted | Draft (future) CIO model agreed |  | Governance model post-project agreed | Setting up 'Shadow Board' (TBC) |  | Stakeholder input on: Development of Governance model - via Working Group
| Set up distinct Working Groups where needed |  | Branding & Identity Working Group Established - to feed into website development initially; Strategic T&F Group established - creating draft high-level vision, mission and objectives | Governance Working Group established | Policies, Portfolio and Funding Model Working Group established
| Appoint Lead Partner & choose central development coordinator | CACRE contract and staffing organised |  | Changes to central staffing model made: MN at .8FTE and RB at .4FTE going forward | [5 empty] | CACRE FCC contributions to organisational overheads; travel and other costs; volunteer expenses; (Recruitment &) salary costs x2 CACRE project management staff (each at .6FTE)
3. Sustainable Development - Developing Vision & Sustainable Development focus | Develop a central Vision for Sustainable Development for the Biosphere |  |  | FBSG (initial) consensus over draft Vision achieved | Central Vision and Objectives discussed through PPFM Working Group | Central Vision and Objectives Finalised |  |  |  | Stakeholder input on: Vision and core Focus/Theme development - Events (pre-Xmas; LAs; launch event)
| Develop central themes/work streams for the Biosphere’s focus |  |  | FBSG (initial) consensus over draft Objectives/ Work streams achieved | Central Vision and Objectives discussed through PPFM Working Group | Central Vision and Objectives Finalised
| Involve relevant research institutions, partnerships and businesses, in developing vision and themes |  |  |  | Initial discussions with select Agri-Tech and research institutions held | Strategy for engagement with research institutions developed
4. Sustainable Development - Developing key BR Objectives | Define key Objectives for Biosphere |  |  | FBSG (initial) consensus over draft Objectives/ Work streams achieved; Stakeholder engagement event/workshops held 18 Dec 2019 | Central Vision and Objectives discussed through PPFM Working Group | Central Vision and Objectives Finalised |  |  |  | Developing a sustainable approach/ 'Building Consensus' - Events (includes pre-Xmas; LAs; launch event) - ; external delivery input no longer needed - TBC
| Align with & influence sustainable development direction taken by the Combined Authority and Local Authorities |  |  | LPAs' relevant key ambitions, strategies and policies identified; identification of evidence base needed to influence LPAs | Social value and economic value brief developed and potential consultants approached | Social value and economic value study commissioned and first phase delivered. | Social value and economic value study - Phase 2 delivered
5. Area - Area identification | Define external boundaries |  |  | Draft map finalised for 6 Nov 2019 UK MAB meeting, to achieve candidate status |  |  | Map consultation with all stakeholders (TBC) | Main map to go with nomination form finalised |  | Research data and information collation; and mapping (probably additional professional input not needed TBC)
| Develop supplementary maps to show landscape development and land use |  | Initial set of supplementary maps finalised, for stakeholder engagement use | Further series of maps created, feeding into document setting out area boundaries and justification, created for candidate status |  |  |  |  | Supplementary maps to go with nomination form finalised
| Consider inclusion of Local Authorities’ boundaries carefully |  |  | Inclusion of LPA boundaries discussed with all key LPAs covering FB area. |  |  | Finalise decision on LPA area inclusion
| Decide on urban and/or rural focus |  |  | Focus explained in document setting out area boundaries and justification, created for candidate status
6. Area - Zonation and mapping | Organise mapping skills & map development logistics |  | Mapping needs for 2-year process identified; capacity for input discussed with Natural England mapping specialist and others
| Solve the ‘Buffer zone challenge’ |  |  | Achieved through 'wet net' proposal - approved by UK MAB as good alternative for buffer zone
| Obtain input from UK MAB Committee and UNESCO MAB Secretariat |  |  | Candidate Biosphere status obtained from UK MAB and UK National Commission for UNESCO |  |  | Teleconferences with and visit(s) to UK Biosphere(s) | Hosting UK MAB meeting - 10 & 11 Nov. |  | Attendance at UNESCO events in UK (and possibly abroad); and to visit other UK-based Biospheres
7. Stakeholders - Stakeholder identification & engagement | Map out & prioritise stakeholders |  | Initial Stakeholder mapping finalised
| Instigate reviewing process for stakeholder mapping |  |  | Key messages for year 1 key stakeholder groups finalised |  | Key messages for year 2 key stakeholder groups finalised
| Get politicians and decision-makers on side |  |  | Initial discussions held with Local Authorities |  | Follow-up discussions held with key Members, Councillors and Officers at relevant LPAs | Follow-up discussions held with key Members, Councillors and Officers at relevant LPAs |  |  | Stakeholder engagement/ 'Building Buy-in' - events including pre-Xmas; LAs; launch event) - possibly Includes external delivery input TBC
| Bring on board other types of stakeholders |  | Initial engagement held with key IDBs | Stakeholder engagement event/workshops held 18 Dec 2019 | Initial engagement held with select sustainability and research organisations |  | Initial engagement with key food industry, water industry and local interest groups; further engagement held with sustainability and research organisations | Initial engagement with key tourism businesses
| Develop methods and tools to get people interested |  | Key engagement events over two years planned in outline |  | Community Forum developed | Community Forum concept and delivery programme adapted due to Coronavirus |  |  | Celebration event
| Engage local communities |  |  |  | Community engagement programme developed | Community engagement and events programme adapted due to Coronavirus |  |  |  | Community consultation & engagement; celebration event (2020/21 Q4)
8. Stakeholders - Communications Plan development | Create a Communications Plan | Comms Plan finalised |  |  |  | Communications Plan, Engagement Plan and Events Plan adapted due to Coronavirus |  |  |  | Communications Plan development
| Develop appropriate communication tools |  |  | Website brief out for tendering | Website finalised | Website launched; new hard copy and online materials produced for community and stakeholder engagement |  |  |  | Website development; hosting costs and website maintenance
| Create brand identity | Social media accounts set up |  | First promotional leaflet created and shared widely | Logo created | New hard copy and online materials produced for community and stakeholder engagement |  |  | Launch Water Works film(s) - TBC | Leaflet and literature production; other digital resources development
9. Future Management - BR Management Policy/Plan development | Map out existing policies/plans/strategies |  |  |  | Key Government, regional and LPAs' polices, strategies, ambitions and action plans collated and embedded in updated strategic documents
| Decide on type of policy/plan to accompany nomination |  |  |  |  | Research by Steven Henry, University of Cambridge MPhil, into alignment with LPAs' policies and understanding other UK Biospheres' policies |  | Policies for future Fens Biosphere agreed |  | Stakeholder consultation on Management Policies/Plan - will need external input
| Explore options for embedding policies with decision-making organisations |  | Fens Biosphere included as key implementation mechanism for Natural Cambridgeshire (Local Nature Partnership)'s Doubling Nature Vision, launched in July 2019 and since adopted by many LPAs |  |  |  | TBC - Event (myth busting bus tour or workshop? ) for Officers and Councillors of LPAs | Hosting UK MAB meeting 10 Nov - inviting LPA reps.
10. Future Management - Alignment & Cooperation with other partnerships etc. | Explore mutually beneficial working relationships |  |  |  | Relevant and overlapping partnerships and initiatives researched. Initial discussions re: future relationships with most key relevant and overlapping initiatives held | Future relationships with Natural Cambridgeshire LNP (and their own emerging CIO) worked out in more detail |  | Arrangements with related partnerships and initiatives established
11. Delivery & Funding model - Portfolio Development for implementation | Bring partnership work under the ‘BR banner’ |  |  |  | Potential for 'Umbrella functioning' first discussed at PPFM Working Group |  |  |  | Portfolio for 2022 and beyond agreed | Stakeholder consultation on: Portfolio development - via Working Group
| Link in with latest developments/opportunities post-BREXIT |  |  |  | Future funding options through e.g. emerging Environment Bill, Agriculture Bill and England Peat strategy embedded in strategic documentation
12. Delivery & Funding model - Sustainable Funding model for implementation | Develop a funding model |  |  |  | Potential funding options collated and initial discussion held through PPFM Working Group |  |  |  | Funding model for 2022 and beyond finalised | Developing sustainable funding model - via Working Group
| Explore bringing in funds through partner-led projects and programmes |  |  |  | Potential for 3rd year funding through DEFRA (via Natural England) fund, through NE's East Anglian Fens Lowland Peat Pilot work |  |  | TBC - apply for external funding for continuation of central coordination? | TBC - apply for external funding for continuation of central coordination?
| Explore funding options from Local Authorities and Combined Authority | [5 empty] | TBC - Start up discussions with relevant decision-makers and/or via relevant associated initiatives
| Explore opportunities for sponsorship from businesses |  |  |  | Discussions with Doubling Nature Natural Capital Investment Plan for Cambridgeshire and Peterborough started for inclusion of Fens Biosphere as delivery model for future businesses' natural capital offsetting and planning options.
Overarching work streams | Nomination paperwork |  |  | Nomination form set-up and supporting documents needs established | Start drafting nomination form |  |  |  | Nomination form consulted on and finalised; Signatures from key decision-makers obtained | Nomination form and supporting documents
| Water Works links |  |  |  |  | Outline Legacy Plan for PPL setting out plans post-project - ready before End-of year 1 Review meeting 7 May 2020 |  |  | Final Legacy Plan developed and feeding into project-wide Water Works Legacy Plan, for PPL | Plus: Some external evaluation input; contingency; and central Water Works comms and M&E activities

## Timeline as per feasibility
| 2018/19 | 2019/20 | 2020/21 | 2021/22
KEY CHALLENGES for Biosphere development towards UNESCO nomination
1. Partnership development
2. Governance model development
3. Developing Vision & Sustainable Development focus
4. Developing key BR Objectives
5. Area identification
6. Zonation and mapping
7. Stakeholder identification & engagement
8. Communications Plan development
9. BR Management Policy/Plan development
10. Alignment & Cooperation with other partnerships etc.
11. Portfolio Development for implementation
12. Sustainable Funding model for implementation
Should be given HIGH PRIORITY in these years
Could be given LOWER PRIORITY in these years